## Risk Register
Volunteer It Yourself
Risk Register
Updated: September 2025
Next review date: September 2026
Created by: Ed Sellwood, COO
Revised by: Ed Sellwood, COO (September 2025)
| Risk Level key: |  | Probability | Impact | Risk Level
|  |  | Low | Low | 1 - low
|  |  | Low | Medium | 2 - low
|  |  | Low | High | 3 - medium
|  |  | Medium | Low | 2 - low
|  |  | Medium | Medium | 3 - medium
|  |  | Medium | High | 4 - high
|  |  | High | Low | 3 - medium
|  |  | High | Medium | 4 - high
|  |  | High | High | 5 - high
ID: | Description of risk: | Key risk indicator: | Probability: | Impact: | Risk level: | Mitigating action(s): | Probability post mitigation: | Impact: | Risk level post mitigation: | Risk owner(s): | Escalation to:
Operational/delivery risks
1 | Not identifying/engaging the target number of clubs/projects in the desired locations | No. of projects confirmed/scheduled | Medium | High | 4 | (1) Working with programme funders, local councils, NGBs, Active Partnerships and trade sector partners/stores to identify and recruit clubs/projects. (2) Working with project partners/funders to set clear project selection criteria. (3) Aligning with national IMD indices of deprivation re target locations and audiences. | Low | High | 3 | Programme Managers | COO
2 | Not recruiting the target number of young people at each project | No. of young people registered/participating | Medium | High | 4 | (1) Provide support to clubs in recruiting young people already associated with the venue/facility. (2) Build ongoing relationships with key youth referral partners - e.g. Job Centre Plus, alternative education providers, youth work organisations such as Catch22, The Prince’s Trust, The Amber Foundation and YMCA, pupil referral units, local schools and colleges, and youth offending teams. (3) Making the registration process for young people as clear and easy to access as possible. (4) Run regular company-wide youth engagement best-practise workshops/sessions. | Low | High | 3 | Youth Engagement Co-ordinators, Project Managers | Programme Managers
3 | Not recruiting/engaging the target number of trade skills mentors | No. of mentors recruited | Medium | High | 4 | Recruit via: (1) Our existing network of trade skills mentors. (2) Our trade sector partners, e.g. Travis Perkins, Toolstation, Dulux and FMB (Federation of Master Builders). (3) Local construction colleges. (4) Trade recommendation sites (e.g. Checkatrade, MyBuilder). (5) Tradespeople who have an existing relationship with the projects/clubs. (6) Other VIY partners (e.g. Job Centre Plus, Men in Sheds) (7) Developing our Peer Mentor network (i.e. offering strong VIY participants the chance to progress into Peer/Assistant Mentor roles). (8) Making the registration process for mentors as clear and easy to access as possible. | Low | High | 3 | Mentors Manager | COO
4 | Not recruiting/engaging the necessary number of City & Guilds trained assessors - and failing to effectively resource our City & Guilds Skills Centre function | No. of trained assessors recruited | Medium | Medium | 3 | Recruit via: (1) Advisory Board (NB: one of the members is a senior figure at City & Guilds). (2) Our existing network of training providers, local construction colleges and assessors. (3) Assessor forums and sector relevant recruitment sites/channels. | Low | Medium | 2 | Skills Manager | COO
5 | Not accrediting our target number of young people | Accreditation rates dropping below 75% of participants | Medium | High | 4 | (1) Ensuring we have (the target numbers of) young people on project sites - see point 2. (2) Identifying young people who have a desire to gain a City & Guilds accreditation. (3) Scheduling multiple assessing days, in case young people aren't on site (for whatever reason). (4) Running multiple accreditation types on projects. (5) Where relevant, offering venues the opportunity to host accredited 'Hub'/workshop activities and sessions. | Low | High | 3 | Project Managers, Skills Manager | Programme Managers
6 | Participants dropping out without completing their projects/individual work plans | % of young people completing projects | Low | High | 3 | (1) Provide detailed information for youth referral partners (and the young people), explaining what a VIY project entails. (2) Brief cohorts of young people, with Project Managers and Lead Mentors, face-to-face prior to activity starting. (3) Work to individual work plans for each young person taking part. (4) Have 'check-ins', between Lead Mentor and young person, at the end of each day. (5) Have check-ins, at least weekly, with the relevant youth referral partner/s. | Low | High | 3 | Project Managers | Programme Managers
7 | Low progressions rates for young people taking part | No. of progressions achieved / proportion of participants progressing | Medium | High | 4 | (1) Capture young people's progression goals as part of project entry process. (2) Driving the progressions element with trade, building and construction sector partners. (3) Working more closely with youth referral partners re the progressions needs of the young people taking part. (4) Tracking longitudinal progression outcomes more effectively | Low | High | 3 | Progressions Manager | Programme Managers
8 | Being unable to access (due to materials shortages or otherwise), store and deliver all the tools and materials required on any given project site | Frequency of project delays due to shortfalls of tools/materials | Medium | High | 4 | (1) Ordering materials ahead of project start dates. (2) Diversifying supply across a broader range of trade sector partners. (3) Bulk ordering and storing materials which can be sent to project sites as/when needed vs sourcing materials on a project-by-project basis. (4) Reusing/recycling materials, including surplus materials from other projects sites. | Low | High | 3 | Project Managers | Programme Managers
9 | Not receiving all in-kind commitments (specifically tools and materials) to enable projects | In-kind value of contributions received | Medium | Medium | 3 | (1) Have formal written agreements in place with trade sector suppliers. (2) Due to our scale up of activities, dilute our reliance on one or two partners by broadening tools/materials requests across the Travis Perkins network/group and, as appropriate, the wider trade, building and construction sector. (3) Including budget to purchase additional/specialist materials if required (at cost price). | Low | Medium | 2 | Project Managers, Programme Managers | Partnerships Director
10 | Unsatisfactory quality of works undertaken | Refurbishment works not signed off by Construction Manager and venue | Medium | High | 4 | (1) Engage Construction Manager on projects. (2) Adhere to any relevant building regulations, permissions and controls. (3) Only use tools and materials from recognised sources (i.e. our programme wide trade sector partners). (4) Ensure mentors have the relevant training/qualifications for the job at hand. (5) Have a system in place, linked to the upfront service level agreement and project Scope of Works, whereby works are checked on a regular and systematic basis. (6) Works signed off by both the Construction Manager and venue. | Low | High | 3 | Construction Manager | COO
11 | Safeguarding issue | An incident or recurring incidents related to safeguarding | Low | High | 3 | (1) All trade skills mentors and assessors are trained on child protection as part of their induction, and they are all DBS checked. (2) Update our Child Protection & Safeguarding Policy annually. (3) We work with - and are audited by - partners/funders (e.g. The Careers & Enterprise Company) on all aspects of safeguarding. | Low | High | 3 | COO (i.e. the DSL) | Chief Exec
12 | Health & Safety issue | An incident or recurring incidents related to Health & Safety | Low | High | 3 | (1) Risk Assessments and Method Statements are created for each project. (2) Venues complete Health & Safety documentation (including confirmation on their insurance cover). (3) Lead Mentors brief young people and complete Due Diligence checklists on site every day. (4) We receive ongoing advice and support from our insurers (Markel) and partners (e.g. Travis Perkins) on all aspects of Health & Safety. (5) We have engage an external Health & Safety consultant. (6) Review/update the Health & Safety Policy annually. | Low | High | 3 | Project Managers, Construction Manager | COO
13 | Evaluation/data collection issue | An incident or recurring incidents related to data collection | Low | Medium | 2 | (1) Established data collection procedures in place, which will be monitored by our Data & Impact Manager and an external evaluator. (2) Training sessions and workshops, led by our Data & Impact Manager, on data collection (for the central team as well as Lead Mentors and assessors). | Low | Medium | 2 | Data & Impact Manager | COO
14 | Data management issue | An incident or recurring incidents related to data management | Low | Medium | 2 | (1) Only collecting and saving data using tools and methods which are approved by our Data & Impact Manager. (2) GDPR training for the entire team. (3) Review/update the GDPR policy annually. | Low | Medium | 2 | Data & Impact Manager | COO
Wider organisational risks
15 | Not recruiting new central team members required to deliver our programmes at scale | No. of central team members recruited (against plans/ requirements) | Medium | High | 4 | Recruit via: (1) Existing recruitment channels that we use (e.g. LinkedIn, Charity People). (2) Partners and supporters advertising roles. (3) Our own networks. | Low | High | 3 | Programme Managers | COO
16 | Key members of the central team leaving | Central team retention rates | Low | Medium | 2 | (1) Support/train central team members as/where required. (2) Promote and/or reward central team members who are excelling in their work. (3) Listen to and act on feedback from central team members. (4) Inform central team members on company-wide aspects such as internal structure, adaptations to our Articles of Association, growth/scaling plans, target markets or clients. | Low | Medium | 2 | Programme Managers | Chief Exec
17 | Not attracting sufficient unidentified/unsecured match funding to enable projects where needed | Match funding not hitting required amounts/targets | Medium | High | 4 | (1) Upfront stakeholder mapping for each project location. (2) Diverse approach to attracting additional support, with dedicated full-time resource to manage the process. (3) Adopting crowdfunding for projects where appropriate, and specifically on Sport England partnership projects. | Low | High | 3 | Partnerships Manager | Chief Exec
18 | Not managing our new and increased portfolio of clients, supporters and funders successfully | Feedback received that clients are receiving insufficient support | Low | High | 3 | (1) Enabling Head of Programmes and Programme Directors to have more client management responsibility and oversight (ensuring clients are managed, enquiries are dealt with promptly and reporting deadlines are met). (2) Generating a client service matrix document. | Low | High | 3 | Partnerships Director | Chief Exec
19 | Given our increased target outputs across 2025-26 and beyond, a sacrifice in the quality and consistency of the delivery of our programmes | Feedback received that programmes are being delivered to a low standard | Low | High | 3 | (1) Implementing a Continuous Improvement Plan (CIP) to monitor and ensure delivery quality is maintained/enhanced, with a specific focus on data collection, evaluation and the recruitment, training and development of staff. (2) Include CIP-specific training as part of staff training and development procedures. (3) Ensure new central team members are managed by another experienced member of the team. (4) In the case of Lead Mentors and assessors, ensure that they are initially mentored by existing/experienced LMs and Skills Manager respectively. | Low | High | 3 | Skills Manager, Data & Impact Manager, Programme Managers | COO
20 | Insufficient cashflow to cover company overheads and programme costs | Cash levels drop below a set amount | Low | High | 3 | (1) Cashflow is monitored on a weekly basis by our Book-keeper, COO and Chief Exec, with figures being reported every six weeks to the Board. (2) A cashflow forecast is updated on a weekly basis, and shared with the Board every six weeks. (3) We hold reserves of at least three months' overhead/costs. | Low | High | 3 | Book-keeper | COO, Chief Exec
21 | Not managing programme budgets effectively | Overspend on individual projects or programmes | Medium | High | 4 | (1) Each programme/project is assigned an individual project number within Xero (our online accounting software). (2) Income and costs are monitored, on a fortnightly basis, on each project. (3) Project Managers also maintain individual project budget trackers. (4) Contingency is built in to project budgets. (5) Where possible, projects form part of a bigger programme so we can compensate for overspend on individual projects. | Low | High | 3 | Programme Managers | COO
22 | Malpractice | Incidents of wrongdoing/fraud are identified | Low | High | 3 | (1) Please refer to our Internal Financial Controls document, which lists our related mitigating actions. | Low | High | 3 | All staff | COO, Chief Exec

## Risk Management Framework
VIY Risk Management Framework
A continuous improvement loop of five stages:
1. Identification: Review risks - amend/update risk register
2. Mitigation: Implementation of risk-related team training and mitigating actions
3. Monitoring/reporting: Ongoing monitoring of key risk indicators
4. Governance: Escalation of issues/concerns by risk owners where necessary
5. Assessment: Assess impact/appropriateness of mitigating actions and any additional actions needed/taken
Stage 5 then leads back into Stage 1